## Sheet1
Iteration #3 | BUILDING USER INTERFACE | Feature | Feature | Feature | Feature
Date of milestone | Dec 16 2024 | Dec 13 2024 | Dec 13 2024 | Dec 14 2024 | Dec 01 2024 | =
Features in scope | Account System & UserInterface_Form | UserInterface_Form | RulerTrack | VideoTrack/Thumbinal Processing | AudioTrack
Features implemented | UserInterface_Form, RullerTrack, VideoTrack, AudioTrack, Thumbinals Processing | Implemented | Implemented | Implemented | Implemented
Features in deficit this Iteration | Video Preview, File Preview
Iteration Comments & Summary | In order to meet year 4 porject requirements, I decided to provide the algorithmical complexity by creating a video editing software instead, completely writing the backend myself without relying on sdk's and using only dependencies such as ffmpeg and so on. This Iteration I have started building the tracks through loading the video. Scope of this and next iteration is to make the form fully interactive providing necessary tracking for video editing software. | The form is fully designed, now I am ready to move on with the backend. | Tracking of seconds video length, furthermore zoom and scale has to be implemented. | Providing user with the uploaded video length based on the ruller, having thumbinals to showcase different parts of a video. Also Thumbinal processing handled with use of ffmpeg. | Same functionality as for Video track but instead providing a generated audio frequency as a result of ffmpeg processing.