## Sheet1
Iteration #4 | BUILDING USER INTERFACE | Feature | Feature | Feature | Feature | Feature | Feature | Feature | Feature | Feature | Feature | Feature
Date of milestone | Dec 16 2024 | Dec 16 2024 | Dec 17 2024 | Dec 18 2024 | Dec 24 2024 | Dec 23 2024 | Dec 23 2024 | Dec 23 2024 | Dec 21 2024 | Dec 21 2024 | Dec 20 2024 | Dec 20 2024
Features in scope | Account System & UserInterface_Form | Video Preview | Segment Logic | Split | Delete | Trim | Cut | Migration from AxWindowsMedia Player to VLC Player | Play | Pause | AutoScroll | Upload
Features implemented | Video Preview, Segment logic, Split, Cut, Trim, Delete, AutoScroll, Play, Pause, Upload, AxWindowsMedia Player to VLC Migration. | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented
Features in deficit this Iteration
Iteration Comments & Summary | In order to meet year 4 porject requirements, I decided to provide the algorithmical complexity by creating a video editing software instead, completely writing the backend myself without relying on sdk's and using only dependencies such as ffmpeg and so on. This Iteration I have started building the tracks through loading the video. Scope of this and next iteration is to make the form fully interactive providing necessary tracking for video editing software. | Lot of work done arround this feature, while it doesn't use network pipe for real-time preview it does use fast render of files to generate when changes are applied to the timeline. Audio and Video are separated giving more control over the editing of the clip. | The whole timeline is devided into segments which gives so many features to happened such as splitting, cutting, trimming, delete of specific clips. Because of this approach all of these features are made possible without the need of implementing different functions for these functionalities. | Lets the user split the uploaded clips on the timeline, deviding them in different parts that then gives the user the posibility of selecting the parts of the clip needed. | Delete segments (parts of the video) that has been selected is now possible opening many features known in video editing through a very handy approach and necessary complexity. | Easy enough to trim the clips and get what you need from it jjust by splitting and removing the unwated segments (parts of the video). | As a result of segmenting and spliting, cutting is made efortless at this point. The logic of deviding clips in parts and then giving the user the ability to remove the selected segments (part of the video) automatically can be considered as cutting functionality in video editing. | The need to do that is because of poor performance of the windows media player, it makes UI stutter and doesn't have the ability to provide fast previews of the clips when user scrolls through video or just change the time. It did require backend changes and mostly all of the logic. | Button to press play and play the video regarding to where the current position is of the tracking line from the time line. | Same functionality but vice versa of the Play feature | Whenever user scrolls near the end of the visible area of the timeline the timeline scrolls according to the direction. | Uploading files triggers thumbnails generation, that generates - stores in a variable images - removes the thumbnails from temp folder - display on the timeline -dispose of the variable. This approach is very convenient because it becomes a light-weight application and doesn't have touse resources in order to store the media filesin memory, this approach ensures high-resolution video to be easy-uploaded with minimal power consumption and performance of the UI Design.