## Sheet1
Iteration #1 | BUILDING USER INTERFACE | Feature | Feature | Feature | Feature | Feature
Date of milestone | Nov 10 2024 | Oct 22 2024 | Oct 28 2024 | Nov 04 2024 | Nov 07 2024 | Nov 08 2024
Features in scope | UI-Design | LogIn_Form. | Loading_Form. | Registration_Form. | FormManager | PasswordRestore_Form.
Features implemented | Implemented: LogIn_Form, Loading_Form, Registration_Form, FormManager | Implemented. | Implemented. | Implemented. | Implemented. | Implemented.
Features in deficit this Iteration | UserInterface_Form.
Iteration Comments & Summary | Smooth corners and borders applied to the forms, interesting feature that lots of developers would recognize inspired from Visual Studio Code app, also it changes the bordering color considering either you are focused or not on the app, Animated background also applied, from simple GIF image I extract each frame and define a custome tick so it looks smooth like 120 frames per second. | First main form to be opened, also includes the methods to be used for next Forms, which will drastically speed up creation of new forms. | Loading_Form created, fully functional and has a logic that does the behaviour you want after completion which will be used on further stages of the application. After successfully optimising the code so it can be shared among the forms, now the smooth animations and round corners with fancy borders are just a 10 seconds question. | Registration_Form created, fully functional and has validation logic for the box inputs, there are 3 more textbox inputs that must have validation which will be created at a later stage of the app development, in short words the UI design is almost there, fully functional with no need for improvements which is a very big step. After the PasswordRestore_Form, I will start working on UserInterface_Form because of all the validation and logic behind the app, the complex parts of the application will be just a matter of time. | After lot of work I started to pay attention to the performance, after serveral tests I realised that the app does not dispose of anything whatsoever which results in unnecessary memory usage, after carefuly analising the problem and the documentation I decided to create a Form Manager that would allow me to easily change between the forms without the need to create new instances and dispose them all the time, also I did write new disposal functions that dispose of any resource as soon as it is not in use which resulted in an increase from 350mb usage or StackOverflows to 100-160 mb constant memory usage. During it lots of cool features were added from the design and navigation perspective for users, ton of bugs fixed, and validation for every single entrie in the app. | All bugs fixed and all validation is now done, the UserInterface_Form would be in deficit for this iteration because next what I will work on is code optimisation, there is a lot of optimisations to be done in order to follow the code standards, everything else such as application performance and resource usage is optimised, for next iteration I will finish the UserInterface_Form first because this is the mos crucial and important part of the application, because of my code features implemented the development of new features will be very easy there will be no need to make validations and look for security threats withing the app, this application should be done by iteration 3 or iteration 4, which will give me time to even better optimise the app and the process of rendering, in short words trying to apply the most recent technologies and best practices if needed.