## Sheet1
Iteration #4 | ADDRESSING SONARQUBE ISSUES/GETTING COVERAGE | Feature | Feature | Feature | Feature | Feature | Feature | Feature | Feature | Feature | Feature
Date of milestone | Mar 30 2025 | Mar 14 2025 | Mar 15 2025 | Mar 16 2025 | Mar 18 2025 | Mar 19 2025 | Mar 22 2025 | Mar 25 2025 | Mar 29 2025 | Mar 29 2025 | Mar 29 2025
Features in scope | Render screen Design & ToolTip Design & Sonar qube analysis addressing | Maintainability issues addressing | Reliability issues addressing | Security issues addressing | Security Hotspot issues addressing | Tests writing | Cache nuget packages CI Update | Render screen fast settings/Templates Design | Render screen advanced settings Design | ToolTip Design & Interaction | Import media functionality & Merging ImportMedia with AddVideoToTimeline
Features implemented | Writing Tests, ToolTip design, Render screen fast settings design, Render screen advanced settings design, Maintainability issues addressing, Reliability issues addressing, Security issues addressing, Import media functionality, Merging ImportMedia with AddVideoToTimeline, Cache nuget packages CI Update. | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented
Features in deficit this Iteration | N/A
Iteration Comments & Summary | This iteration has been very productive, I've been able to hit the mark of 93 test methods, covering 20.5% of the entire code through comprehensive testing,I've addresed all the issues in the Security, Reliability, Maintainability and also Security Hotspots, the code is now 100% clean (85-90 issues has been addressed), since I was addressing the naming conventions/method naming/formatting and more. Other than that new functionality and user-interactions has been added such as tooltip new features, and Render screen design. At this stage the Render screen is devided in 2 different compartments one being FastSettings/Templaes and another one Advanced Settings (for proffesionals use only). For the tooltip the import media correctly generates a thumbnail and reflects the thumbnail and the filename for fast access and inclusion into the timeline handling any possible outcomes and exceptions. In this Iteration I dont have any deficit what so ever, it actually has far more features implemented than planned | Maintainability issues addressing, this compartment has been completed within 10-12 commits, as a result 0 maintainability isses, for future I would sugest students make CI first before starting working on the actual application since from that point I fix them asap . | Very few issues but still complex issues to address, also 100% of the issues addressed. | Hard coded credentials for admin user for testing purposes moved to .config file, also other problems such as DDOS protection have been applied however this were shared issues with Reliability, e.g. timing out limit setup for regex asserts. | Interesting part of the analysis, it would tell me some passed os parameters that I had to rewrite in order to make the secure enough, more like fixing security holes and finding workarrounds for this specific framework. | 64-70 new Unit Tests methods, which gave +15% for overall code coverage. Was aiming for 100% however I've been advised to work on new features instead since this would be enough to cover for testing section. | Before nuget packages dotnet checking was taking arround 4 minutes to finish, after the cache implemented it shrinked down to 1 minute max. | This is fully design at this stage, the only thing remaining is handling user interactions and running the necessary cmd using ffmpeg with the already created function, but should be rewriten so it handles multiple parameter passing. | Partially finished and it is going to be finished in the next day or two, holding the same exact description as for fast settings however with more advanced options for render. | Gave new style and restructured code, now it is fully usable and works as a normal tooltip bar, at this stage only writing the functionalities for them is remained. | When a video is imported user has two choices, either to import necessary metadata only for future use via drag-&-drop to the timeline or directly importing it including placing the pseudo media on the timeline, this gives flexibility to the user, while holding a history of what has been imported in the specific project.