## Sheet1
Iteration #4 | ADDRESSING SONARQUBE ISSUES/GETTING COVERAGE | Feature | Feature | Feature | Feature | Feature | Feature | Feature | Feature | Feature | Feature | Feature | Feature | Feature | Feature | Feature | Feature | Feature | Feature
Date of milestone | Apr 13 2025 | Mar 30 2025 | Mar 31 2025 | Apr 1 2025 | Apr 2 2025 | Apr 2 2025 | Apr 2 2025 | Apr 3 2025 | Apr 4 2025 | Apr 5 2025 | Apr 6 2025 | Apr 7 2025 | Apr 8 2025 | Apr 9 2025 | Apr 9 2025 | Apr 9 2025 | Apr 10 2025 | Apr 11 2025 | Apr 12 2025
Features in scope | ToolTip Functionalities/CD/Render Screen Fast Settings/Templates/Advanced Settings /Save Project/Final Touches | Control Panel | Fast Settings Design | Advanced Settings Design | Template functionality for render settings | Fast Settings Rendering | Advanced Settings Rendering | Dynamic progress bar | Preview Custom Height | Preview Custom Width | Preview Custom FrameRate | Fast Preview Mode | Resync Functionality | Save Project | Save As Project | Open .rnc project | File Integrity Check for Default Templates | Duplication Issues Addressing | Duplication Issues Addressing
Features implemented | Control Panel, Fast Settings Design, Advanced Settings Design, Template functionality for render settings, Fast Settings Rendering, Advanced Settings Rendering, Dynamic Progress Bar, Preview Custom Height, Preview Custom Width, Preview Custom FrameRate, Fast Preview Mode, Resync Functionality (for fast preview mode), Save project, Save as project, Open .rnc project, Duplication Issues Addressing, More Maintainability issues addressing, File Integrity Check for Default Templates. | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented | Implemented
Features in deficit this Iteration | ShortKeys Functionality, CD, Packaging using Wix, Reflect visually the opening of the saved .rnc project file, Mute VideoTrack, Mute AudioTrack, Drag&Drop functionality from imported media to time-line.
Iteration Comments & Summary |  | Control Panel gives the user full control over the video/audio track just by using he's mouse or he's keyboard by using tab to switch between button or clicking with the mouse. It has thin it 11 buttons therefore 11 new functionalities, ranging from segment selection to scrolling/splitting/removing/ and so on. | The Design is a mix of combo boxes and inputs that would allow the user to understand very easy what quality is picking, non-required previous experience, very user intuitive and naming. | Same as the fast settings however gives the user a more granular control and following the naming conventions known as video editing preferences when rendering. This can be enabled by clicking the check box "enable advanced settings", it also holds a warning at the label noting that you must be a professional in order to create a successfull combination of settings. | This holds some default templates that follows the standards of uploading clips to youtube, specific settings that would specify the settings, it applies both to advanced and fast settings. The functionality holds CRUD functionality which means you can create a template, update it and remove it, however it is not allowed to remove the default premade templates. | It checks firstly wether there is already a file with the same nam within the chosen directory (default is C:/users/videos/Rencloud_Outputs/) e.g. if there is a file nmed output.mp4 then it would set the name output_1 within the rendering settings, or it would ask if you would like to overwrite the existing one. The rendering is triggered based on settings chosen, predefined cmd commands within the code for each of the options. It also uses a special command version that returns the progress of the rendering therefore allowing to retreive the information and display as a dynamic progress bar. | All of the features mentioned for the fast settings. On top of that since it is advanced settings it lets the user to pick custom height and width at granular level therefore a functionality has been implemented that is working with Aspect Ratio combo box while holding a check box that either allow or not proportional scaling, the proportionality is based on the aspect ratio. Anything else is the same as for fast settings however, it was required to write a separate function to run the command properly with more specifications about the output the user wants. | Based on the ffmpeg output the bar converts the data into understandable data for the dynamic progress bar to understand, and by using it it provides exact progress from start to finish, the loading is precise and not an estimated one. | The user now can specify specific height for the preview when it is generating, so based on how powerfull your machine is you can pick your desired value, higher - slower rendering but higher quality. | The same exact description as for Height however it changes the Width, the values are predefined therefore there is some sort of proportionality between these 2 values. | The same exact description as for last 2 functionalities, however this one is responsible for how smooth the video preview playback is, these 4 functionalities are tightly implemented using the main engine of the application they are basically included within it. | There is a checkbox at the top of the media player VLC, that if checked will render the current project from scratch making sure it is synched with the segments properly, and won't point anymore to the original file path, but to the newly preview generated file, this has some problems thats why it is a setting, since the framework is old and has its limitations, while VLC returning time stamps are once 40 ms, after making changes the ffmpeg maths would outsynch the preview with the current structure of the segments, therefore times to times there must be done a resync process in order to make sure you see the reflections precisely. The logic is that if you have set yout optimal preview custom settings that generates fast enough the render, it would result that processing the original file which could be 4k res, would take much longer, while having a output with ur optimal settings and using that one to reflect changes drastically speeds up the processing of the previewing (this has its own exclusive variable it does not overwrite the original segmentaton data structure). This basically required to have a second look at the engine, that resulted in more major changes to it, which became somehow more performat at the moment. I also had a gc collect before, but sonar qube was complaining about it, and now the application runs on 400-500 mb in RAM, with gc collect it would work at 200-250, I would leave it, but I want no realiability issues. | As mentioned in the last fast preview mode, the user must make resync time-to-time, I couldve make it automatic, however this would be unexpected for the user and therefore the user can do it by pressing a button whenever he consideres it is needed. What happens is that the preview output is regenerated from scratch pointing back to the original file rather than preview file. Resulting in resynched preview with the timeline segments. And then user can continue using the fast preview as it was. | Save project acts as any normal software, if there is a file it for this project then it would save it there, if none created before it would open the explorer and let the user pick where to save it, it creates a file type .rnc (rencloud) which is generated using Newtonsoft.Json package, allowing the application to save all the necessary data needed. | The same description as for save project, however the logic is different, it would always open the explorer and let the user pick where to save the file, and then repoint to this file for future (Save Project) -> functionality. | This functionality has been partially completed, it does load everything that is needed, the only thing remaining for a complete version of it is creating a speciifc function that would reflect the data on the timeline (visually display). | This would check wether some templates are missing or if even the templates JSON file is missing, it would also granularly check for each of the templates, therefore it would replace/create the ones missing making impossible to be corrupted or make any erros. I could just use a file within my project build however I wanted to experiment and created a very basic file integrity check that generates the templates data on run-time of the software. | Lots of duplications because of the file integrity check, which required some attention, it wasn't crucial however sonar qube doesn't have an option to let the user pick which functions are considered for duplications check, so I had to address mainly all of them. | More than 35 more maintainability issues if not 50 from coding new features, not critical tho. At the moment I must address 0.7% of duplications and 16 more small maintainability issues.