## Sheet1
Iteration #1 | BUILDING USER INTERFACE | Feature | Feature | Feature | Feature | Feature
Date of milestone | Nov 10 2024 | Oct 22 2024 | Oct 28 2024 | Nov 10 2024 | Nov 10 2024 | Nov 10 2024
Features in scope | UI-Design | LogIn_Form. | Loading_Form. | UserInterface_Form. | Register_Form. | PasswordRestore_Form.
Features implemented | Implemented: LogIn_Form, | Implemented. | Not Implemented. | Not Implemented. | Not Implemented. | Not Implemented.
Features in deficit this Iteration | Loading_Form, UserInterface_Form, Register_Form, PasswordRestore_Form.
Iteration Comments & Summary | Smooth corners and borders applied to the forms, interesting feature that lots of developers would recognize inspired from Visual Studio Code app, also it changes the bordering color considering either you are focused or not on the app, Animated background also applied, from simple GIF image I extract each frame and define a custome tick so it looks smooth like 120 frames per second. | First main form to be opened, also includes the methods to be used for next Forms, which will drastically speed up creation of new forms. | Loading_Form created, fully functional and has a logic that does the behaviour you want after completion which will be used on further stages of the application. After successfully optimising the code so it can be shared among the forms, now the smooth animations and round corners with fancy borders are just a 10 seconds question.
Iteration #2
Date of milestone
Features in scope
Features in deficit this Iteration
Iteration Comments & Summary
Iteration #3
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary
Iteration #4
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary
Iteration #5
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary
Iteration #6
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary