## Sheet1
Iteration #1 | BUILDING USER INTERFACE | Feature | Feature | Feature | Feature
Date of milestone | Dec 1 2024 | Nov 20 2024 | Nov 26 2024 | Nov 27 2024 | Dec 01 2024
Features in scope | Account System & UserInterface_Form | UsernameValidation_Tests | PasswordValidation_Tests | EmailValidation_Tests | SendingValidInformation_Tests
Features implemented | UsernameValidation_Tests, PasswordValidation_Tests, EmailValidation_Tests, SendingValidInformation_Tests | Implemented | Implemented | Implemented | Implemented
Features in deficit this Iteration | UserInterface_Form
Iteration Comments & Summary | To successfully bring and work on some critical components it was not the best iteration, yet I did find a replacement of my initial ideas and successfully managed to bring them in a very comprehensive and granular way. Making the tests allowed me to spot critical bugs within the app that I was even surprised to meet, overall over than 45 test methods that checks this features I think this iteration played a very big role because critical components of the application has been tested and yes there was bugs that I had to fix right away.